## Project Planner
Nutrition Tool
[6 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66
| Project Management/Requirements | 1 | 6 | bar: PERIODS 1 to PERIODS 6
1.1 | Complete project management documentation | 1 | 4 |  |  | 0%
1.2 | Stakeholder Interviews and surveys | 1 | 4 |  |  | 0%
1.3 | Research/purchase tools/software for project | 5 | 2 |  |  | 0%
| System Frameworks and Design | 7 | 18
2.1 | Data structure Design | 7 | 1 |  |  | 0%
2.2 | Define dictionary structures | 8 | 2 |  |  | 0%
2.3 | Functions Outlines | 8 | 1 |  |  | 0%
2.4 | User interface design | 8 | 2 |  |  | 0%
2.5 | Wireframe creation | 10 | 2 |  |  | 0%
2.6 | user flow design | 12 | 1 |  |  | 0%
2.7 | Interface Structure Design | 13 | 2 |  |  | 0%
2.8 | Outline visual design | 15 | 2 |  |  | 0%
2.9 | Meeting 1 | 17 | 1 |  |  | 0%
2.1 | Integrate meeting Changes | 18 | 1 |  |  | 0%
2.11 | Debug 1 | 18 | 4 |  |  | 0%
2.12 | Integrate Additional Software | 21 | 4 |  |  | 0%
| Development | 25 | 28
3.1 | Implement Data Structures | 25 | 1 |  |  | 0%
3.2 | Create Dictionaies for data | 26 | 2 |  |  | 0%
3.3 | Implement/code Function LoadData | 28 | 2 |  |  | 0%
3.4 | Implement/code Function FoodSearch | 30 | 3 |  |  | 0%
3.5 | Implement/code Function NutritionalBreakdown | 30 | 3 |  |  | 0%
3.6 | Implement/code Function RangeFilter | 31 | 3 |  |  | 0%
3.7 | Implement/code Function NutritionalLevel | 32 | 3 |  |  | 0%
3.8 | Implement/code Function FoodComparison | 33 | 3 |  |  | 0%
3.9 | Code Tool | 36 | 7 |  |  | 0%
3.1 | Create User Interface | 43 | 6 |  |  | 0%
3.11 | Integrate with Functions and Data Structures | 49 | 3 |  |  | 0%
3.12 | Meeting 2 | 52 | 1 |  |  | 0%
| Testing | 53 | 13
4.1 | Integrate meeting Changes | 53 | 2 |  |  | 0%
4.2 | Debug 2 | 54 | 5 |  |  | 0%
4.3 | Integrate Additional Software | 59 | 1 |  |  | 0%
4.4 | User Acceptance Testing | 60 | 3 |  |  | 0%
4.5 | Performance testing | 62 | 3 |  |  | 0%
5 | Deploy System | 65 | 1 |  |  | 0%